## Tripura
Sr No | Actionable Points | Timelines | Status of Compliance | Remarks
1 | Test Assam | At the earliest | Non-Complied | 15 paisa/unit rebate is being given (same as prior to meeting). Further incentives yet to be decided by Discoms
2 | Pursue for effective use of data analytics by field engineers | At the earliest | Non-Complied | DISCOMs issued directions to field offices, however, outcome of referred cases yet not received.
3 | Install check meters for atleast 5% consumers | Immediately | Non-Complied | 1 % check meters installed
4 | REC to conduct another round of Whatsapp feedback survey | Immediately | Complied | REC has completed repeat survey
5 | Complete smart metering on C&I consumers | July'26 | Work in Progress | • Progress yet to accelerate. • Current progress :Comm- 24 %, Industrial-15% (Last meeting : Commercial-20% & Industrial-8%)
6 | Availability of all data analytic reports, SLA Module and online invoicing | April'26 | Non-complied | • Data Analytic reports and SLA Modules developed, data validation in process. • Online invoicing system is yet to be developed
7 | Integration of all legacy IT systems with MDM | At the earliest | Work in progress | Legacy Billing System, Consumer Complaint Centre have been integrated with MDM. AMR data of DT & Feeders yet to be integrated
8 | Dedicated cyber security cell with trained manpower in all Discoms | At the earliest | Work in Progress | Complied for AVVNL, whereas in process for JVVNL & JdVVNL
9 | Reconciliation of scope for DT metering | 10th April'26 | Non-Complied | • Recoincilation done for JdVVNL and JVVNL. • For AVVNL, cross verification of surveyed qty is in process.
10 | Integration with NFMS for correct SAIFI/SAIDI information | April'26 | Complied | All integration related issues resolved now
11 | Expedite feeder segregation and HH electrification -complete by Dec'26. | Dec'26 | Work in Progress | Acceleration required as low pace of progress (Only 2% feeders segregated & 4% HH electrified since meeting)
12 | Pursue for NABL accreditation of CTL labs. | At the earliest | Non-Complied | No significant action taken by DISCOM for accrediation
13 | Adherence of Quality monitoring guidelines | At the earliest | Complied | Discoms constituted teams for carrying out random quality checks
14 | DISCOMs to claim Return on Equity in their tariff petition. | At the earliest | Non-Complied | No significant efforts for complying, provided by Discoms
15 | JdVVNL to take specific efforts to reduce AT&C losses and ACS-ARR gap. | At the earliest | Work in Progress | • Reforms like ToD tariffs, FPPAS, Regulatory Surcharge already taken up • Infra works to reduce losses expedited (Feeder segregation, new substation, re-conductoring, capacitors at Agri consumer, etc) • Planning for Tariff rationalization, Debt restructuring, Renewable energy expansion, IT/OT integration, BEES for long-term sustainability.
16 | Operation of old and non- operational TPS as synchronous condenser & use of grid forming inverters | At the earliest | Work in Progress | • DCPP, Dholpur and GLTPP, Giral were identified to be used as synchronous condenser. • BHEL visited Dholpur and submitted report to MoP through CEA.

## Rajasthan
Sr No | Actionable Points | Timelines | Status of Compliance | Remarks
1 | Explore suitable incentives for pre-paid consumers | At the earliest | Non-Complied | 15 paisa/unit rebate is being given (same as prior to meeting). Further incentives yet to be decided by Discoms
2 | Pursue for effective use of data analytics by field engineers | At the earliest | Non-Complied | DISCOMs issued directions to field offices, however, outcome of referred cases yet not received.
3 | Install check meters for atleast 5% consumers | Immediately | Non-Complied | 1 % check meters installed
4 | REC to conduct another round of Whatsapp feedback survey | Immediately | Complied | REC has completed repeat survey
5 | Complete smart metering on C&I consumers | July'26 | Work in Progress | • Progress yet to accelerate. • Current progress :Comm- 24 %, Industrial-15% (Last meeting : Commercial-20% & Industrial-8%)
6 | Availability of all data analytic reports, SLA Module and online invoicing | April'26 | Non-complied | • Data Analytic reports and SLA Modules developed, data validation in process. • Online invoicing system is yet to be developed
7 | Integration of all legacy IT systems with MDM | At the earliest | Work in progress | Legacy Billing System, Consumer Complaint Centre have been integrated with MDM. AMR data of DT & Feeders yet to be integrated
8 | Dedicated cyber security cell with trained manpower in all Discoms | At the earliest | Work in Progress | Complied for AVVNL, whereas in process for JVVNL & JdVVNL
9 | Reconciliation of scope for DT metering | 10th April'26 | Non-Complied | • Recoincilation done for JdVVNL and JVVNL. • For AVVNL, cross verification of surveyed qty is in process.
10 | Integration with NFMS for correct SAIFI/SAIDI information | April'26 | Complied | All integration related issues resolved now
11 | Expedite feeder segregation and HH electrification -complete by Dec'26. | Dec'26 | Work in Progress | Acceleration required as low pace of progress (Only 2% feeders segregated & 4% HH electrified since meeting)
12 | Pursue for NABL accreditation of CTL labs. | At the earliest | Non-Complied | No significant action taken by DISCOM for accrediation
13 | Adherence of Quality monitoring guidelines | At the earliest | Complied | Discoms constituted teams for carrying out random quality checks
14 | DISCOMs to claim Return on Equity in their tariff petition. | At the earliest | Non-Complied | No significant efforts for complying, provided by Discoms
15 | JdVVNL to take specific efforts to reduce AT&C losses and ACS-ARR gap. | At the earliest | Work in Progress | • Reforms like ToD tariffs, FPPAS, Regulatory Surcharge already taken up • Infra works to reduce losses expedited (Feeder segregation, new substation, re-conductoring, capacitors at Agri consumer, etc) • Planning for Tariff rationalization, Debt restructuring, Renewable energy expansion, IT/OT integration, BEES for long-term sustainability.
16 | Operation of old and non- operational TPS as synchronous condenser & use of grid forming inverters | At the earliest | Work in Progress | • DCPP, Dholpur and GLTPP, Giral were identified to be used as synchronous condenser. • BHEL visited Dholpur and submitted report to MoP through CEA.
17 | CEA to facilitate Bhadla-Bikaner 400 kV bay equipment for uprating terminal bays of refurbished RVPN line, from PGCIL on loan basis | At the earliest | Work in Progress | • RVPN approved uprating of terminal bays equipments of several 400 kV lines (including Bhadla-Bikaner line). • NIT for uprating of isolator issued on 26.05.2026 and NIT for CT/CB) will be issued in June-2026
18 | Conduct a repeat simulation RAP exercise (yearwise) for upto FY 2029-30 and plan necessary capacity. Target commissioning of 6000 MWh BESS projects before timeline (Sep-Oct 2027) to meet the power demand. | At the earliest | Work in Progress | • RUVITL carrying Simulation exercise for RAP 2029-30 in consultation with CEA. CEA furnished output of STELLAR tool & being examined. • RVUNL is regularly monitoring ongoing 6000 MWh BESS projects to achieve commissioning before Oct' 2027.
19 | Expedite construction of 765 KV Pugal GSS and associated lines so that proposed Solar Park of 2,450 MW with storage may be commissioned by June 2028. | At the earliest | Work in Progress | • PFFCL appointed as BPC for implementing 765 kV GSS Bikaner (Pugal) in TBCB mode • Allowed for implementation in 38th Coordination Committee meeting of power sector companies held on 07.05.2026 • RFP for bidding is under approval

## Uttar Pradesh
Sr No | Actionable Points | Timelines | Status of Compliance | Remarks
1 | Explore suitable incentives for pre-paid consumers | At the earliest | Non-Complied | 15 paisa/unit rebate is being given (same as prior to meeting). Further incentives yet to be decided by Discoms
2 | Test for Actionable Point UP | At the earliest | Non-Complied | DISCOMs issued directions to field offices, however, outcome of referred cases yet not received.
3 | Install check meters for atleast 5% consumers | Immediately | Non-Complied | 1 % check meters installed
4 | REC to conduct another round of Whatsapp feedback survey | Immediately | Complied | REC has completed repeat survey
5 | Complete smart metering on C&I consumers | July'26 | Work in Progress | • Progress yet to accelerate. • Current progress :Comm- 24 %, Industrial-15% (Last meeting : Commercial-20% & Industrial-8%)
6 | Availability of all data analytic reports, SLA Module and online invoicing | April'26 | Non-complied | • Data Analytic reports and SLA Modules developed, data validation in process. • Online invoicing system is yet to be developed
7 | Integration of all legacy IT systems with MDM | At the earliest | Work in progress | Legacy Billing System, Consumer Complaint Centre have been integrated with MDM. AMR data of DT & Feeders yet to be integrated
8 | Dedicated cyber security cell with trained manpower in all Discoms | At the earliest | Work in Progress | Complied for AVVNL, whereas in process for JVVNL & JdVVNL
9 | Reconciliation of scope for DT metering | 10th April'26 | Non-Complied | • Recoincilation done for JdVVNL and JVVNL. • For AVVNL, cross verification of surveyed qty is in process.
10 | Integration with NFMS for correct SAIFI/SAIDI information | April'26 | Complied | All integration related issues resolved now
11 | Expedite feeder segregation and HH electrification -complete by Dec'26. | Dec'26 | Work in Progress | Acceleration required as low pace of progress (Only 2% feeders segregated & 4% HH electrified since meeting)
12 | Pursue for NABL accreditation of CTL labs. | At the earliest | Non-Complied | No significant action taken by DISCOM for accrediation

## Assam
Sr No | Actionable Points | Timelines | Status of Compliance | Remarks
1 | Test Assam | At the earliest | Non-Complied | 15 paisa/unit rebate is being given (same as prior to meeting). Further incentives yet to be decided by Discoms
2 | Pursue for effective use of data analytics by field engineers | At the earliest | Non-Complied | DISCOMs issued directions to field offices, however, outcome of referred cases yet not received.
3 | Install check meters for atleast 5% consumers | Immediately | Non-Complied | 1 % check meters installed
4 | REC to conduct another round of Whatsapp feedback survey | Immediately | Complied | REC has completed repeat survey
5 | Complete smart metering on C&I consumers | July'26 | Work in Progress | • Progress yet to accelerate. • Current progress :Comm- 24 %, Industrial-15% (Last meeting : Commercial-20% & Industrial-8%)
6 | Availability of all data analytic reports, SLA Module and online invoicing | April'26 | Non-complied | • Data Analytic reports and SLA Modules developed, data validation in process. • Online invoicing system is yet to be developed
7 | Integration of all legacy IT systems with MDM | At the earliest | Work in progress | Legacy Billing System, Consumer Complaint Centre have been integrated with MDM. AMR data of DT & Feeders yet to be integrated
8 | Dedicated cyber security cell with trained manpower in all Discoms | At the earliest | Work in Progress | Complied for AVVNL, whereas in process for JVVNL & JdVVNL
9 | Reconciliation of scope for DT metering | 10th April'26 | Non-Complied | • Recoincilation done for JdVVNL and JVVNL. • For AVVNL, cross verification of surveyed qty is in process.
10 | Integration with NFMS for correct SAIFI/SAIDI information | April'26 | Complied | All integration related issues resolved now
11 | Expedite feeder segregation and HH electrification -complete by Dec'26. | Dec'26 | Work in Progress | Acceleration required as low pace of progress (Only 2% feeders segregated & 4% HH electrified since meeting)
12 | Pursue for NABL accreditation of CTL labs. | At the earliest | Non-Complied | No significant action taken by DISCOM for accrediation
13 | Adherence of Quality monitoring guidelines | At the earliest | Complied | Discoms constituted teams for carrying out random quality checks
14 | DISCOMs to claim Return on Equity in their tariff petition. | At the earliest | Non-Complied | No significant efforts for complying, provided by Discoms
15 | JdVVNL to take specific efforts to reduce AT&C losses and ACS-ARR gap. | At the earliest | Work in Progress | • Reforms like ToD tariffs, FPPAS, Regulatory Surcharge already taken up • Infra works to reduce losses expedited (Feeder segregation, new substation, re-conductoring, capacitors at Agri consumer, etc) • Planning for Tariff rationalization, Debt restructuring, Renewable energy expansion, IT/OT integration, BEES for long-term sustainability.
16 | Operation of old and non- operational TPS as synchronous condenser & use of grid forming inverters | At the earliest | Work in Progress | • DCPP, Dholpur and GLTPP, Giral were identified to be used as synchronous condenser. • BHEL visited Dholpur and submitted report to MoP through CEA.